## Features
Project: hailua.com.vn
Team: 5
ID | Feature Name | Description | Remark
UC01 | Add Product as Admin | Admins can add new products with details and categories.
UC02 | Browse and Search | Users can navigate, filter, and search for products.
UC03 | Shopping Cart | Users manage selected items before checkout.
UC04 | Browser compatibility | Verify compatibility across Chrome, Firefox, Opera, and Edge.
UC05 | Login as end user | End users log in securely to access personalized features.
UC06 | Register as end user | New users create accounts with personal details.
UC07 | Purchase for products in Cart | Users complete purchases from their cart.

## Test cases
Function/Feature ID | Case ID | Test case name | Test step | Expected Result (ER) | Actual Result | Status | Tester | Tested Date | Remark
Function 01: Add Product as Admin
UC01 | UI01 | Validate Mandatory Fields | 1. Enter unavailable categories 2. Upload image: " " 3. Enter Product Name: " " 4. Enter description: " " 5. Enter price: " " 6. Enter quantity: " " 7. Select Shipping: " " 8. Click "CREATE PRODUCT" button | System displays appropriate error messages for each missing mandatory field. | 1. Created successfully but did not add data to the database. 2. No error message. | Fail | MQĐạt | 2024-03-01
UC01 | UI02 | Add Product with Valid Data | 1. Enter available categories 2. Upload image: "hinhdep.png" 3. Enter Product Name: "Nhẫn Hot" 4. Enter description: "Làm từ bạc" 5. Enter price: "300" 6. Enter quantity: "10" 7. Select Shipping: "Yes" 8. Click "CREATE PRODUCT" button | Product is successfully added without errors. | The same ER | Pass | MQĐạt | 2024-03-01
UC01 | UI03 | Add Product with Invalid Image Format | 1. Enter available categories 2. Upload image: "chudep.txt" 3. Enter Product Name: "Nhẫn Hot" 4. Enter description: "Làm từ bạc" 5. Enter price: "300" 6. Enter quantity: "10" 7. Select Shipping: "Yes" 8. Click "CREATE PRODUCT" button | 1. System shows error for unsupported file format. 2. Did not add data to the database. | 1. No error message is displayed 2. Still adding data to the database | Fail | MQĐạt | 2024-03-01
UC01 | UI04 | Verify Admin Role Restrictions | 1. Log in as a non-admin user. 2. Find "Create Product" feature. 3. Access via direct URL without admin rights. | 1. Non-admin users cannot access "Add Product" feature. 2. Unable to access URL | 1. Access to "Add Product" is denied for non-admin users. 2. Unable to access URL 3. Returns to the home page | Pass | MQĐạt | 2024-03-01
UC01 | UI05 | Verify Product Addition Persistence | 1. Add a product and check product listing. 2. Check for the added product in the database. | 1. Product added by admin is displayed in the product list. 2. Product details match those submitted during addition. | 1. Added product is visible in the product list. 2. Product details correspond to the submitted data. | Pass | MQĐạt | 2024-03-01
Function 02: Browse and Search
UC02 | UI01 | Search for valid product | 1. Enter keyword/phrase: "Dây chuyền" in the search bar. 2. Click on the "Search" button | Search results relevant to the keyword are shown. | 1. Shows how many results were found 2. Search results relevant to the keyword are shown. | Pass | DQBảo | 2024-03-01
UC02 | UI02 | Search for invalid product | 1. Enter a non-existent/random keyword: "@!@" in the search bar. 2. Click on the "Search" button | The system returns a message indicating "No Products Found" | "No Products Found" message displayed. | Pass | DQBảo | 2024-03-01
UC02 | UI03 | Search with blank characters | 1. Enter " " in the search bar. 2. Click on the "Search" button | The system returns nothing | Crash app | Fail | DQBảo | 2024-03-01
UC02 | UI04 | Browse Products by Category | 1. Select category that exists Ex: "Ring" | Products within the selected category are displayed. | Products displayed match the selected category. | Pass | DQBảo | 2024-03-01
UC02 | UI05 | Filter Search Results | 1. Apply filters (price range) to the search results. Ex: "$40 to 59" | Products matching the applied filters are displayed. | Only partial or no products match the applied filters. | Fail | DQBảo | 2024-03-01
Function 03: Shopping Cart
UC03 | UI01 | Add Product to Cart | 1. Start from the product page. 2. Click on the "Add to Cart" button for a specific product. 3. Check the Cart page to verify if the product has been successfully added. | The product should be added to the cart. | The product appears in the cart with the correct quantity. | Pass | DQBảo | 2024-02-01
UC03 | UI02 | Remove Product from Cart | 1. Ensure there is at least one product in the cart. 2. Click on the remove button of that product. 3. Confirm the removal of the product. | The product should be removed from the cart. | The product disappears from the cart. | Pass | DQBảo | 2024-02-01
UC03 | UI03 | Calculate Total Amount in Cart | 1. Ensure there are at least two products in the cart with specific prices. 2. Check and note down the price of each product. 3. Confirm the calculation of the total amount in the cart. | The total amount in the cart should equal the sum of the prices of all products. | The displayed total amount should match the sum of the noted prices. | Pass | DQBảo | 2024-02-01
UC03 | UI04 | Test Cart Saving Functionality | 1. Add several products to the cart. 2. Log out of the account or close the browser. 3. Log back in and check if the products in the cart are retained. | The products in the cart should be saved after the user logs back in. | The products in the cart persist after the user logs back in. | Pass | DQBảo | 2024-02-01
Function 04: Browser compatibility
UC04 | UI01 | Check Compatibility on Chrome | 1. Access diamondhandstore using the Chrome browser. 2. Browse and perform basic functionalities on the website. | All functions should work correctly and smoothly on the Chrome browser. | Functions perform correctly, and the website displays accurately on Chrome. | Pass | DQBảo | 2024-02-01
UC04 | UI02 | Check Compatibility on Firefox | 1. Access diamondhandstore using the Firefox browser. 2. Browse and perform basic functionalities on the website. | All functions should work correctly and smoothly on the Firefox browser. | Functions perform correctly, and the website displays accurately on Firefox. | Pass | DQBảo | 2024-02-01
UC04 | UI03 | Check Compatibility on Opera | 1. Access diamondhandstore using the Opera browser. 2. Browse and perform basic functionalities on the website. | All functions should work correctly and smoothly on the Opera browser. | Functions perform correctly, and the website displays accurately on Opera. | Pass | DQBảo | 2024-02-01
UC04 | UI04 | Check Compatibility on Edge | 1. Access diamondhandstore using the Edge browser. 2. Browse and perform basic functionalities on the website. | All functions should work correctly and smoothly on the Edge browser. | Functions perform correctly, and the website displays accurately on Edge. | Pass | DQBảo | 2024-02-01
Function 05: Login as end user
UC05 | UI01 | Log in with correct username and password | 1. Enter User Name: "dat@gmail.com" 2. Enter Password: "dat123123" 3. Click "LOGIN" button | Authenticated | The same ER | Pass | MQĐạt | 2024-03-01
UC05 | UI02 | Log in with incorrect username | 1. Enter User Name: "dat@gmail.com" 2. Enter Password: "dat123456" 3. Click "LOGIN" button | 1. Unauthenticated 2. A wrong user-account notice will be displayed | 1. Disallows the user to proceed and 2. The error message "Something went wrong" displayed | Pass | MQĐạt | 2024-03-01
UC05 | UI03 | Log in with incorrect password | 1. Enter User Name: "dat@gmail.com" 2. Enter Password: "dat123456" 3. Click "LOGIN" button | 1. Unauthenticated 2. A wrong password will be displayed | 1. Disallows the user to proceed and 2. The error message "Invalid Password" displayed | Pass | MQĐạt | 2024-03-01
UC05 | UI04 | Login with blank User name and Password | 1. Enter User Name: " " 2. Enter Password: " " 3. Click "LOGIN" button | 1. Disallows the user to proceed and 2. The error message should be displayed | 1. Disallows the user to proceed and 2. The error message "Please fill out this field" displayed | Pass | MQĐạt | 2024-03-01
UC05 | UI05 | Log in with incorrect email | 1. Enter User Name: "datmai" 2. Enter Password: "dat123123" 3. Click "LOGIN" button | 1. Disallows the user to proceed and 2. The error message should be displayed | 1. Disallows the user to proceed and 2. The error message "Please include an '@' in the email address. 'datmai' is missing an '@'" displayed | Pass | MQĐạt | 2024-03-01
Function 06: Register as end user
UC06 | UI01 | Register with valid information | 1. Enter Name: "Khang Ngo" 2. Enter email: "KNgo@gmail.com" 3. Enter Password: "123456" 4. Enter Phone: "0905050509" 5. Enter Address: "Chung cu Him Lam" 6. Enter Favorite sports: "bong bau duc" | 1. Account successfully created 2. Returns the login page | The same ER | Pass | DQBảo | 2024-03-01
UC06 | UI02 | Register with one or more blank fields | 1. Enter Name: "Khang Ngo" 2. Enter email: " " 3. Enter Password: " " 4. Enter Phone: " " 5. Enter Address: " " 6. Enter Favorite sports: "bong bau duc" | 1. Disallows the user to proceed and 2. At the blank field(s) warning message will be display | The same ER | Pass | DQBảo | 2024-03-01
UC06 | UI03 | Register with username has already been used | 1. Enter Name: "Khang" 2. Enter email: "KNgo@gmail.com" 3. Enter Password: "1234567" 4. Enter Phone: "0905050500" 5. Enter Address: "Chung cu Giai Viet" 6. Enter Favorite sports: "bong bau cua" | 1. Disallows the user to proceed 2. The message notify that usename exists should be displayed | The same ER | Pass | DQBảo | 2024-03-01
UC06 | UI04 | Register with invalid email format | 1. Enter Name: "Khang" 2. Enter email: "KNgogmailcom" 3. Enter Password: "1234567" 4. Enter Phone: "0905050500" 5. Enter Address: "Chung cu Giai Viet" 6. Enter Favorite sports: "bong bau cua" | 1. Disallows the user to proceed 2. At the email field there will be a message notify that the email is wrong | The same ER | Pass | DQBảo | 2024-03-01
UC06 | UI05 | Register with invalid phone format | 1. Enter Name: "Khang" 2. Enter email: "KNgo@gmail.com" 3. Enter Password: "1234567" 4. Enter Phone: "abcd" 5. Enter Address: "Chung cu Giai Viet" 6. Enter Favorite sports: "bong bau cua" | 1. Disallows the user to proceed 2. At the phone field there will be a message notify that the phone is not valid | The account was still created successfully | Fail | DQBảo | 2024-03-01
Function 07: Purchase for products in Cart
UC07 | UI01 | Purchase with valid information | 1. Enter Card Number: "4242424242424242" 2. Enter Expiration Date: "0442" 3. Enter CVV: "424" | 1. Payment success 2. Save this payment in order history | The same ER | Pass | MQĐạt | 2024-03-01
UC07 | UI02 | Purchase with one or more blank fields | 1. Enter Card Number: " " 2. Enter Expiration Date: "0442" 3. Enter CVV: " " | 1. Disallows the user to proceed and 2. At the blank field(s) warning message will be display | The same ER | Pass | MQĐạt | 2024-03-01
UC07 | UI03 | Purchase with invalid card number | 1. Enter Card Number: "123456789010" 2. Enter Expiration Date: "0442" 3. Enter CVV: "424" | 1. Disallows the user to proceed 2. At the Card Number field there will be a message notify that the card number is not valid | The same ER | Pass | MQĐạt | 2024-03-01
UC07 | UI04 | Purchase with invalid expiration date | 1. Enter Card Number: "4242424242424242" 2. Enter Expiration Date: "0411" 3. Enter CVV: "424" | 1. Disallows the user to proceed 2. At the Expiration Date field there will be a message notify that the expiration date is not valid | The same ER | Pass | MQĐạt | 2024-03-01
UC07 | UI05 | Purchase with invalid CVV | 1. Enter Card Number: "4242424242424242" 2. Enter Expiration Date: "0442" 3. Enter CVV: "123" | 1. Disallows the user to proceed 2. At the CVV field there will be a message notify that the security code is not valid | The same ER | Pass | MQĐạt | 2024-03-01